WO-MENT

Minutes of the 2nd Transnational Project Meeting

| Dates of meeting: | 03 – 05 May, 2014 |
| --- | --- |
| Meeting location: | Hamrun, Malta |
| Participants: | Maria Unzue - Area de la Mujer Estella-Lizarra Larraitz Trinkado - Area de la Mujer Estella-Lizarra Esperanza Vidal - Area de la Mujer Estella-Lizarra Areti Chatzi – Responsible Citizens Stergios Zarkanelas - Responsible Citizens Andrzej Bialko - Multikultura Marek Chołoniewski - Multikultura Krystyna Chołoniewska - Multikultura Krzysztof Ridan - Multikultura Radosława Ridan – Multikultura Cynthia Tomasuolo – The Geminarie Group Louis Tomasuolo – The Geminarie Group Partners from EUROKOM – not present |
| Minute taker: | Cynthia Tomasuolo The Geminarie Group |

Issues discussed

Contractual Obligations towards NA – The Progress Report: Each partner is to submit the progress report to their respective NAs by the 30.06.2014 It was agreed that: PART A is to be filled by ES: deadline – 15.06.2014 PART B is to be filled by respective partners – 30.06.2014 Deadline to send report to NA – 30.06.2014 Supporting Documents required: Project Meetings: Spain and Malta Documents: Certificates, Agenda, Minutes, List of Attendance, Evaluation Report Project Work: Logo Start-Up electronic Leaflet in EN Contacts Database Mock Up/Skeleton Website Dissemination Material at Local/National level (if available) Documents are to be uploaded on the dropbox account – created by EL by 10.05.2014 All partners to submit supporting documents by 01.06.2014 RE: Dropbox Account: EL is to create two folders – one entitled Projects with 5 different sub-folders for the project meetings and another folder for documentation Project Logo - Branding, creating awareness, drawing attention, being recognised and associated with the WO-MENT project: ALL Partners are to submit to ES and upload on dropbox TWO logos for Votation by the 12.05.2014. MT to send link to the Online Voting on 13.05.2014 Voting from ALL Partners by not later than 16.05.2014 Contact Database for Dissemination: ALL Partners are to send 15 contact details of potential stakeholders involved in education and lifelong learning at European, Regional, National and Local Level. MT to send template by 07.05.2014 ALL Partners to fill in contact form and upload on dropbox by 26.05.2014 Project Website - Hosting all publicly available information of the project along with an area dedicated to e-learning: Partners discussed the possibility of having a professional website rather than a blog. MT pointed out that Web-based communication should be the main dissemination instrument for the WO-MENT project thus a website providing detailed information concerning the project aims, progress and news should be developed. EL pointed out that the website should also have the technical capacity to allow upload of online ICT Courses. This would not be possible on a blog. Purchase of a Domain: ES is responsible for the purchase of the internet domain. EL to check availability of domain names by 16.05.2014: www.wo-ment.eu www.wo-ment.project.eu The proposal from Greece: EL suggested sub-contracting a designed for the development / maintenances of the website inclusive of an e-learning tool. Approximate cost is of EUR 2000.00 divided by the partners. PL did not agree with the proposal because of the cost involved. PL is to provide feedback on their position vis-à-vis the project proposal and the website by 10.05.2014 Site Map and Quotations: It was agreed that EL and PL send to all partners a mock up and a quotation in relation to the website MT and ES – to submit the sitemap by the 10.05.2014 On the site map, EL and PL are to send a mock up and quote before the end of May, 2014. Start-Up Electronic Leaflet – introducing the project objectives and the planned activities. It shall be concentrated on the general project’s purpose. Its aim is to announce the project, its goals and planned outcomes MT to prepare the template and content for the e-leaflet by the 24.05.2014 E-Leaflet to contact information regarding Project Description Aims and Objectives Partners Contact ALL to send feedback and approve e-leaflet for dissemination by the 01.06.2014 E-Learning Tool The e-learning tool is to include ICT Basic Courses – Mail, Social Media, Internet and Safety of Use, Windows, Word The tool will also include an e-mentoring service and a repository of documents on: How to prepare a CV and a motivation letter; Basic Steps upon entry in the host country – Country Profile incl. statistical information Counselling Tips Job Opportunity Links Contact Database The Mobility of Mentors and Mentees: Partners agreed about the mobility of a maximum number of TWO Mentors per country for the final conference in Greece. Guide for Mentoring Partners agreed to have mentoring session between the mentees and the mentors in respective countries in between September 2014 to April 2015. ES to send guide for mentoring by 30.05.2014 ALL Partners to send feedback on guide by the 07.06.2014 PL to finalize and adopt feedback from all partners by the 14.06.2014 Templates for the Mentoring process: MT to submit reporting templates by the 12.05.2014 ALL Partners to send feedback on templates by 16.05.2014 Gantt Chart EL to send Gantt Chart by 12.05.2014 Follow-Up: Skype meeting schedule on the 3rd June, 2014 @ 14.00 1. Position of Italy vis-à-vis project and partners 2. Website versus Blog Next Project Meeting: Krakow, Poland 01 – 04 September, 2014