WO-MENT

Minutes of the 3th Transnational Project Meeting

| Dates of meeting: | 03.09.2014 till 06.09.2014 |
| --- | --- |
| Meeting location: | Kraków, Poland |
| Participants: | Andrzej Bialko Loredana Panetta Alessandra Tuzza Marcello Giovanni Orlando Bruno Panetta Caterina Praticò Ettore Chistian De Pietro Giulia Cataldo Areti Chatzi, Stergios Zarkanelas, Eirini Roupa, Ilias Mpampatzelios, Teresa Sáez Barrao Cynthia Tomasuolo Anita Camilleri, Maria Stella Tomasuolo Maria Pelion. Magdalena HernandezSalazar Larraitz Trinkado Uranga |
| Minute taker: | Andrzej Bialko - Multikultura |

Issues discussed

Contractual obligations of each partner: The following contribution of partners was agreed during the meeting: Translation to national languages of the project website will be done till deadline – 15.10.2014 Development of each partner's site in support for the migrant women Changes in the project website and sub pages Supporting Documents required: Project Meetings: Spain, Malta, Poland Annexes: Certificates, Agenda, Minutes, List of Attendance, Evaluation Report Project Work: Approval of electronic Leaflet in EN Contacts Database by all partners Website corrections and testing in natural environment New sub pages proposed and accepted Dissemination Material at Local/National level Support for migrant women materials collected All partners to submit supporting translation and documents by 15.10.2014 Intensify collaboration between partners via SKYPE conferences and e-mails. The due time for each partner to answer the e-mail is 3 days Contact Database for Dissemination: ALL Partners are to send 15 contact details of potential stakeholders involved in education and lifelong learning at European, Regional, National and Local Level. ALL Partners to fill in contact form and upload on dropbox by 15.10.2014 ALL the format of the CV and interview translate 15.10.2014 ALL provide the links to the local respective websites by 15.10.2014 ALL contact relevant points and people working with migrants by 15.10.2014 Project Website - Hosting all publicly available information of the project along with an area dedicated to e-learning: Partners discussed the possibility of correcting the professional project website. Consortium approved the Web-based communication should be the main dissemination instrument for the WO-MENT project thus a website providing detailed information concerning the project aims, progress and news should be further developed also after the project end. Multikultura will provide the online ICT Courses according to the website technical capacity. The website home page will be provided with national flags to the sub pages for each partner The log in function will be removed as unnecessary. The special counter will be installed for statistical data. Start-Up Electronic Leaflet – introducing the project objectives and the planned activities. It shall be concentrated on the general project’s purpose. Its aim is to announce the project, its goals and planned outcomes MT to prepare the template and content for the additional e-leaflet by the 15.10.2014 E-Leaflet to contact information regarding Project Description Aims and Objectives Partners Contact ALL to send feedback and approve the new e-leaflet for dissemination by the 15.10.2014 E-Learning Tool The e-learning tool is to include The tool will also include an e-mentoring service and a repository of documents on: How to prepare a CV and a motivation letter; Basic Steps upon entry in the host country – Country Profile incl. statistical information Counselling Tips Job Opportunity Links Contact Database The Mobility of Mentors and Mentees: Partners agreed about the mobility of a maximum number of TWO Mentors per country for the final conference in Greece. Guide for Mentoring Partners agreed to have mentoring session between the mentees and the mentors in respective countries in between September 2014 to April 2015. ES to send guide for mentoring by 15.10.2014 Templates for the Mentoring process: ES to submit reporting templates by the 15.10.2014 Follow-Up: Skype meeting schedule on the 16rd Oct, 2014 @ 14.00 current project issues. Translations etc Next Project Meeting: Italy 02 – 04 February, 2015